## Tracker
Module | Screen | Widgets | Functionality | Status | Stages | Done | Info | Bug
Splash | splash | logo animation | 5 sec logo animation, route to onboarding, login, permissions, or home from saved token | Online + Offline | success | TRUE
Onboarding | onboarding | image , dots, buttons | 5 slides (attendance, check in/out, offices, history, devices) + Already have account / Book a demo | Online + Offline | success | TRUE
Demo | book a demo | form, text field, phone field, dropdown, button | name + email + phone + industry, | Online | success | TRUE | offline submit is not queued
| request success | image, button | thank-you, back to onboarding | Online + Offline | success | TRUE
| terms | text body, back button | BDUI terms from server, cached on phone | Online + Offline | success | TRUE
| privacy | text body, back button | BDUI privacy from server, cached on phone | Online + Offline | success | TRUE
Auth | login email | text field, button | validate email / phone / id, check email exists | Online | success | TRUE
| login password | text field, checkbox, button | password + remember me, save token, company, offices, role | Online | success | TRUE | OTP login not built
| forgot password | text field, button | send reset email | Online | success | TRUE
| forgot success | sheet, button | check-email confirmation | Online | success | TRUE
Permission | enable permission | hero image, permission list, button | request Location, Notifications, Motion, then go home + register device | Online + Offline | success | TRUE
Clock | clock | check-in button | check in | Online + Offline | success / unsuccessful | TRUE | blocked if out of range, mock GPS, or no trusted time
| clock | break button | break out (start break) | Online + Offline | success / unsuccessful | TRUE | only after check in; policy break length shown
| clock | check-in button | break in (end break) | Online + Offline | success / unsuccessful | TRUE | button label End Break while on break
| clock | check-out button | check out | Online + Offline | success / unsuccessful | TRUE | ends the day; needs a check in first
| clock | range badge | in range / out of range (~50m) | Online + Offline | success | TRUE
| clock | offline banner | show no-internet banner | Offline | success | TRUE
| clock | queue + sync toast | save punch offline and sync when back | Online + Offline | success / unsuccessful | TRUE
| clock | timeline list | today's check in, break, check out cards | Online + Offline | success | TRUE | refreshes about every 30s when online
| clock | toast | success / error after punch | Online + Offline | success / unsuccessful | TRUE | checked in, break started, out of range, non-working day
| punch details | timeline sheet | open today's punch times + locations | Online + Offline | success | TRUE
| office details | location sheet | office name, address, photo, range | Online + Offline | success | TRUE
Attendance | history | month header | change month / year | Online + Offline | success | TRUE
| history | summary card | working days count | Online + Offline | success | TRUE | counted on phone from month list
| history | summary card | absent / leaves count | Online + Offline | success | TRUE
| history | summary card | late check-in count | Online + Offline | success | TRUE | after 9:15 AM in app
| history | summary card | late check-out count | Online + Offline | success | TRUE | before 6:00 PM in app
| history | day list | day row with check in / check out times | Online + Offline | success | TRUE | warning icon if check out missing
| history | weekend card | group consecutive weekends | Online + Offline | success | TRUE
| history | pull to refresh | reload month from server or cache | Online + Offline | success / unsuccessful | TRUE
| holiday | info sheet | weekend / holiday info | Online + Offline | success | TRUE | no extra request
| day details | timeline sheet | check in time + location | Online + Offline | success / unsuccessful | TRUE
| day details | timeline sheet | break out time + location | Online + Offline | success / unsuccessful | TRUE
| day details | timeline sheet | break in time + location | Online + Offline | success / unsuccessful | TRUE
| day details | timeline sheet | check out time + location | Online + Offline | success / unsuccessful | TRUE
| add / edit | form sheet | request check-in time change | Online | success / unsuccessful | TRUE | waits for manager; queued if offline
| add / edit | form sheet | request break-out time change | Online | success / unsuccessful | TRUE | waits for manager; queued if offline
| add / edit | form sheet | request break-in time change | Online | success / unsuccessful | TRUE | waits for manager; queued if offline
| add / edit | form sheet | request check-out time change | Online | success / unsuccessful | TRUE | waits for manager; queued if offline
Alerts | employee alerts | empty state | placeholder: Alerts Coming soon |  | unsuccessful | FALSE | list, filters, API, tab badge
| manager alerts | empty state | placeholder: Alerts Coming soon |  | unsuccessful | FALSE | device approval / rejection still pending
More | profile | profile header | show photo, name, job, department | Online + Offline | success / unsuccessful | TRUE | cached when offline
| profile | profile header | change / remove photo | Online | success / unsuccessful | TRUE
| profile | settings chip | open account information | Online + Offline | success | TRUE
| profile | logout card | logout (clears this phone only) | Online + Offline | success | TRUE | POST /auth/logout not called
| account | accordion list | profile fields (name, email, phone, job) | Online + Offline | success / unsuccessful | TRUE | company-managed; not editable here
| account | accordion list | company rules (working days, times, allowed/not) | Online + Offline | success / unsuccessful | TRUE
| offices | location card list | see assigned offices | Online + Offline | success | TRUE | from login / current user
| offices | location card list | set default office | Online + Offline | success | TRUE
| offices | range text | in range / out of range for default office | Online + Offline | success | TRUE
| linked devices | device list | list Requested / Active / Pending / Blocked | Online + Offline | success / unsuccessful | TRUE | cached list
| linked devices | device list | remove a device | Online | success / unsuccessful | TRUE
| change password | form, checklist, button | current + new + confirm | Online | success / unsuccessful | TRUE
| reminders | switch + time picker | check in reminder | Online + Offline | success | TRUE | local notification
| reminders | switch + duration picker | check in missed reminder | Online + Offline | success | TRUE
| reminders | switch + time picker | check out reminder | Online + Offline | success | TRUE
| reminders | switch + duration picker | check out missed reminder | Online + Offline | success | TRUE
| reminders | switch + time picker | break time reminder | Online + Offline | success | TRUE
| reminders | switch + time picker | break time ended reminder | Online + Offline | success | TRUE
| reminders | switch + duration picker | longer break reminder | Online + Offline | success | TRUE
| reminders | switch + duration picker | very long attendance reminder | Online + Offline | success | TRUE
| terms | text body | terms of use from server, cached | Online + Offline | success / unsuccessful | TRUE
| privacy | text body | privacy policy from server, cached | Online + Offline | success / unsuccessful | TRUE
| help | form, phone field, button | name, email, phone, department, issue | Online | success / unsuccessful | TRUE
| help sent | image, button | ticket sent confirmation | Online + Offline | success | TRUE
| device blocked | message, buttons | retry register + logout | Online | success / unsuccessful | TRUE
Overview | overview | overview card | present today count | Online | success / unsuccessful | TRUE | tap can open team attendance filter
| overview | overview card | active count | Online | success / unsuccessful | TRUE
| overview | overview card | on break count | Online | success / unsuccessful | TRUE
| overview | overview card | late check-in count | Online | success / unsuccessful | TRUE
| overview | overview card | absent count | Online | success / unsuccessful | TRUE
| overview | action tile | add location | Online | success / unsuccessful | TRUE
| overview | action tile | add employee | Online | success / unsuccessful | TRUE
| overview | directory row | view all employees | Online | success | TRUE
| overview | directory row | view all locations | Online | success | TRUE
| overview | pull to refresh | reload dashboard | Online | success / unsuccessful | TRUE | no offline dashboard cache
Employees | all employees | search bar | search by name | Online | success | TRUE | no offline list
| all employees | filter chips | status filter | Online | success | TRUE
| all employees | filter chips | location filter | Online | success | TRUE
| all employees | stats bar | active / pending / disabled counts | Online | success | TRUE
| all employees | employee list | open employee profile | Online | success | TRUE
| add employee | form sheet | invite by email + location | Online | success / unsuccessful | TRUE
| invite sent | dialog | invite confirmation | Online + Offline | success | TRUE
| employee profile | profile sheet | view name, role, photo, contact | Online | success / unsuccessful | TRUE
| employee profile | share buttons | call / WhatsApp / email / SMS | Online + Offline | success | TRUE | uses phone/email from profile
| employee profile | photo picker | change employee photo | Online | success / unsuccessful | TRUE
| employee profile | settings tile | linked devices | Online | success / unsuccessful | TRUE
| employee profile | settings tile | reset password | Online | unsuccessful | FALSE | tile present; flow still pending
| employee profile | settings tile | default offices & locations | Online | success / unsuccessful | TRUE
| employee profile | settings tile | check in / out timing | Online | success / unsuccessful | TRUE
| employee profile | settings tile | working days | Online | success / unsuccessful | TRUE
| employee profile | settings tile | break timing | Online | success / unsuccessful | TRUE
| employee profile | settings tile | deactivate / activate account | Online | success / unsuccessful | TRUE
| employee attendance | month header, summary card, day list | that employee month history | Online | success / unsuccessful | TRUE
| employee attendance | day details | that employee check in / break / check out | Online | success / unsuccessful | TRUE
| default locations | location list, checkbox, radio | assign offices to employee | Online | success / unsuccessful | TRUE
| linked devices | device list | see / manage that employee phones | Online | success / unsuccessful | TRUE
Locations | all locations | location card list | list offices | Online | success / unsuccessful | TRUE | no offline list
| all locations | plus button | open add location | Online | success | TRUE
| location overview | stats card | today present / active / break / late / absent | Online | success / unsuccessful | TRUE
| location overview | member list | people at this office today | Online | success / unsuccessful | TRUE
| location setup | settings tile | add employees to this location | Online | success / unsuccessful | TRUE
| location setup | settings tile | set up location (map pin) | Online | success / unsuccessful | TRUE
| location setup | settings tile | check in / out timing + grace | Online | success / unsuccessful | TRUE
| location setup | settings tile | working days | Online | success / unsuccessful | TRUE | hours in week/day still pending API
| location setup | settings tile | break timing | Online | success / unsuccessful | TRUE
| location setup | delete / deactivate | remove or deactivate office | Online | success / unsuccessful | TRUE
| map setup | map, search | pin office + geofence radius | Online | success / unsuccessful | TRUE
| new location | form sheet | create office name + address | Online | success / unsuccessful | TRUE
| delete location | dialog | confirm remove office | Online | success / unsuccessful | TRUE
Manager Attendance | team list | date header | pick day | Online | success | TRUE | no offline team list
| team list | search bar | search employee | Online | success | TRUE
| team list | filter chips | status filter | Online | success | TRUE
| team list | filter chips | location filter | Online | success | TRUE
| team list | employee list | live team day (check in time + status) | Online | success / unsuccessful | TRUE
| team list | pull to refresh | reload team day | Online | success / unsuccessful | TRUE
| attendance details | timeline sheet | check in time + location + flags | Online | success / unsuccessful | TRUE
| attendance details | timeline sheet | break out time + location + flags | Online | success / unsuccessful | TRUE
| attendance details | timeline sheet | break in time + location + flags | Online | success / unsuccessful | TRUE
| attendance details | timeline sheet | check out time + location + flags | Online | success / unsuccessful | TRUE
| attendance details | summary card | duration and punch flags | Online | success | TRUE
| edit attendance | form sheet | edit check in (applies now) | Online | success / unsuccessful | TRUE | manager edit is direct, not a request
| edit attendance | form sheet | edit break out (applies now) | Online | success / unsuccessful | TRUE
| edit attendance | form sheet | edit break in (applies now) | Online | success / unsuccessful | TRUE
| edit attendance | form sheet | edit check out (applies now) | Online | success / unsuccessful | TRUE
Note on G1: TRUE = done. Google Sheets: select G2:G → Insert → Checkbox.

## Legend
Employee + manager functionality is one row each (check in, break out, break in, check out, …).
Clock / Attendance / More = employee (Clock is also the manager Clock tab).
Overview / Employees / Locations / Manager Attendance = manager.
Open in Excel, or upload this .xlsx to Google Sheets.

## Summary
Module | Screens / functions | Done | Pending
Splash | 1 | 1 | 0
Onboarding | 1 | 1 | 0
Demo | 4 | 4 | 0
Auth | 4 | 4 | 0
Permission | 1 | 1 | 0
Clock | 11 | 11 | 0
Attendance | 17 | 17 | 0
Alerts | 2 | 0 | 2
More | 25 | 25 | 0
Overview | 10 | 10 | 0
Employees | 21 | 20 | 1
Locations | 13 | 13 | 0
Manager Attendance | 15 | 15 | 0
Total | 125 | 122 | 3